## Gantt Chart
PSU e-ISKOLAR SCHOLARSHIP MANAGEMENT SYSTEM
CAPSTONE PROJECT TIMELINE - SYSTEM DEVELOPMENT, USABILITY TESTING AND MANUSCRIPT
Pangasinan State University - Lingayen Campus ¦ BSIT ¦ JUNE 2026 - DECEMBER 2026
ACTIVITIES | STATUS | JUNE 2026 |  |  |  | JULY 2026 |  |  |  |  | AUGUST 2026 |  |  |  | SEPTEMBER 2026 |  |  |  | OCTOBER 2026 |  |  |  |  | NOVEMBER 2026 |  |  |  | DECEMBER 2026
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1
A. SYSTEM DEVELOPMENT - PSU e-ISKOLAR SCHOLARSHIP MANAGEMENT SYSTEM
Requirements gathering and SRS v2 finalization | Completed | bar: JUNE 2026 W1 to JUNE 2026 W2
Database schema design and EF Core migrations (FR-9) | Completed
Authentication, RBAC and user management (FR-1, FR-7, FR-8) | Completed | bar: JUNE 2026 W3 to JULY 2026 W1
Scholar profiling and academic performance tracking (FR-1, FR-12) | Completed
Self-service document submission and file validation (FR-2) | Completed | bar: JULY 2026 W1 to JULY 2026 W3
Records management and verification workflow (FR-3) | Completed
Monitoring dashboards, analytics and reporting (FR-4, FR-5) | Completed | bar: JULY 2026 W3 to AUGUST 2026 W1
Announcements, notifications and real-time updates (FR-6, FR-13, FR-14) | Completed
Submission deadlines, compliance windows and messaging (FR-16, FR-17) | Completed | bar: AUGUST 2026 W1 to AUGUST 2026 W2
Financial release and one-time grant tracking (FR-22) | Completed
Bulk account import, advanced search, privacy and consent (FR-15, FR-10, FR-19) | Completed | bar: AUGUST 2026 W2 to AUGUST 2026 W3
System settings, two-factor authentication and security hardening (NF-7) | Completed
Code audit and defect remediation (24 defects closed) | Completed | bar: JULY 2026 W5 to AUGUST 2026 W4
Automated test suite build-up (64 to 142 passing tests, NFR-5.4) | Completed
System consultation with adviser and panel | In progress | bar: SEPTEMBER 2026 W1 to SEPTEMBER 2026 W3
Scholarship renewal workflow (FR-18.2, FR-18.3) | Planned
Renewal worklist and dashboard drill-down (FR-18.4) | Planned | bar: SEPTEMBER 2026 W3 to SEPTEMBER 2026 W4
Accessibility remediation - labels and keyboard access (NFR-3.5) | Planned
Theme tokens, lint clean-up and response DTOs (NFR-3.3, 5.6, 5.7) | Planned | bar: SEPTEMBER 2026 W3 to OCTOBER 2026 W2
Dependency advisory fix and CI audit gate (NFR-7.9) | Planned
Load, concurrency and cross-browser testing (NFR-4.1, 4.3, 6.1) | Planned | bar: OCTOBER 2026 W1 to OCTOBER 2026 W2
Deployment, uptime monitoring and scheduled backup (NFR-2.1, 2.3) | Planned
System finalization, schema and API reference documents (NFR-5.5) | Planned | bar: OCTOBER 2026 W4 to NOVEMBER 2026 W2
B. USABILITY TESTING AND ISO 25010 EVALUATION
Preparation of the ISO 25010 acceptability instrument | Planned | bar: SEPTEMBER 2026 W4 to OCTOBER 2026 W1
Validation of the research instrument by experts | Planned
Pilot usability test / dry run with sample respondents | Planned | bar: OCTOBER 2026 W3
USABILITY TESTING - 30 scholars, 10 coordinators, 10 IT experts | Planned
Tabulation and statistical analysis of usability results | Planned | bar: NOVEMBER 2026 W1 to NOVEMBER 2026 W2
System refinement based on usability findings | Planned
C. MANUSCRIPT WRITING, CONSULTATION AND DEFENSE
Chapters 1-3 revision and finalization | Completed | bar: JUNE 2026 W1 to JULY 2026 W1
Update of the review of related literature and studies | Completed
Chapter 3 - methodology and system design documentation | Completed | bar: JULY 2026 W1 to JULY 2026 W4
Adviser consultation on Chapters 1-3 | Completed
System specifications and implementation status audit write-up | In progress | bar: AUGUST 2026 W3 to SEPTEMBER 2026 W1
Chapter 4 - Results and Discussion writing | Planned
PRE-FINAL DEFENSE | Planned | bar: OCTOBER 2026 W1
Chapter 5 - Summary, Conclusions and Recommendations | Planned
Chapters 4 and 5 consultation with adviser | Planned | bar: OCTOBER 2026 W2 to NOVEMBER 2026 W2
Abstract, preliminaries, CV and other parts | Planned
IMRaD discussion and write-up | Planned | bar: NOVEMBER 2026 W2
Preparation for final defense | Planned
FINAL DEFENSE | Planned | bar: NOVEMBER 2026 W4
Manuscript revisions and hardbound submission | Planned
LEGEND
System development - completed
System development - planned
Quality, testing and deployment work
Usability testing and ISO 25010 evaluation
Manuscript writing and consultation
Milestone / defense
Status as of 25 August 2026. Weeks follow the calendar weeks of each month; October has five reporting weeks.
Prepared by:
KENNETH REY TABLANG
BSIT IV - Capstone Project
Noted by:
CARLA CARMELA P. RAMOS, DIT
Subject-in-charge